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1. The types and quantities of machinery to be used shall be determined based on the characteristics of the work to be performed and the work schedule.
2. Whenever possible, it is preferable to use the same machine for both excavation and loading operations.
3. During earthwork operations, the adequacy of the number of machines being used shall be monitored. If the number of machines is insufficient or excessive, the Site Manager shall initiate corrective/preventive actions.
4. Before excavation begins, the topsoil (vegetative soil) on the excavation area shall be excavated separately and transported to the location specified in the project.
5. Fill works shall primarily be carried out using soil obtained from the excavation, provided that it is available, suitable and economically feasible to transport to the fill area. If the fill cannot be constructed using excavated soil, suitable fill material may be obtained by purchasing it from an external source.
6. Before starting filling operations, the topsoil (vegetative soil) on the fill area shall be excavated and transported to the location specified in the project. The resulting base shall then be loosened, watered and compacted. After completion of these operations, the base shall be ready for filling.
7. Before excavation/filling operations, the thickness of the topsoil (vegetative soil) to be removed shall not be less than the thickness specified in the project documents.
8. Placement/spreading shall be carried out in layers having the thickness specified in the relevant specifications.
9. If required by the relevant authorities, a trial section shall first be carried out for compaction works to determine the number of roller passes required to achieve the specified compaction level. Compaction shall then be performed based on the results obtained from this trial.
10. The above-mentioned trial shall be repeated whenever the characteristics of the material delivered for filling change.
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